# Agentic Programming Hackathon

| Organizers | agentic.tm, UPT, UVT |
| --- | --- |
| Part of | olimpiada-ai.ro |
| Date | May 15–17, 2026 |
| Venue | TBD (Timisoara) |
| Participants | ~100 high school students, Romania west region |
| Teams | 2–4 members, BYOD |

## Concept

### Theme: HUMAN IN THE LOOP

The central theme of this hackathon is Human in the Loop — building AI agents that work with humans, not instead of them.

Students build agents that reason, plan, use tools, and take actions — but with a human guiding, reviewing, approving, or collaborating at critical points. The agent proposes, the human decides. The agent drafts, the human refines. The agent acts, the human supervises.

This isn’t a constraint — it’s the point. The most powerful AI systems in production today are human-in-the-loop. Teaching students this from day one sets them apart.

Students get API credits from multiple providers and choose their own stack. No restrictions on tools or models.

### What we need to finalize

| # | Question | Options |
| --- | --- | --- |
| 1 | Friday evening or Saturday morning start? | Fri evening = more hacking hours. Sat morning = simpler logistics. |
| 2 | Teams pre-formed or matchmaking? | A) Pre-formed only. B) Matchmaking workshop Day 1. C) Mix — register as team or solo. |
| 3 | Venue? | UPT / UVT / External. Need: WiFi for 100, power outlets, projector, breakout rooms. |
| 4 | How specific is the challenge brief? | A) Broad (“build a HITL agent”). B) 2–3 specific problems. C) Fully open. |
| 5 | Judging criteria & prizes? | Criteria: technical depth, real-world impact, HITL design quality, creativity. Prize structure TBD. |
| 6 | Food & accommodation? | Meals only / full board / meals + dorm partnerships. |
| 7 | Registration? | Google Form / olimpiada-ai.ro page / Eventbrite. |
| 8 | Prerequisites? | Basic programming required? Or we teach everything from zero? |

## Mentors

We need mentors for the weekend. Three pools:

| Source | What they bring | Contact |
| --- | --- | --- |
| agentic.tm (200+ Discord, 500+ LinkedIn) | Hands-on agentic AI / LLM API expertise | Vlad |
| UPT faculty & PhD students | Academic CS depth, GPU cluster access | TBD |
| UVT faculty & PhD students | AI/ML research, venue support | TBD |

Action: Recruit 10 mentors. ~1 mentor per 10 students.

## Credits

Credits are solved. We need $1,500–3,000 total. Multiple paths available, detailed in credit-programs.md.

What students sign up for before the event (free, no sponsorship needed):

| Provider | Free credits | Source |
| --- | --- | --- |
| Together AI | $100/student | together.ai/pricing |
| xAI (Grok) | $25/student | getaiperks.com |
| Gemini | 1,000 req/day (Flash-Lite) | ai.google.dev |
| Mistral | 1B tokens/mo, all models | mistral.ai/pricing |
| Groq | Free tier, ultra-fast | console.groq.com |
| GitHub Models | 50 req/day GPT-4o | docs.github.com |

Self-serve alone = ~$14,000 across 100 students. That’s 5–10x what we need.

Sponsor applications (in progress):

| Provider | Program | Deadline | Apply |
| --- | --- | --- | --- |
| OpenAI | Hackathon Support | April 10 | openai.com/form/hackathon-support |
| Anthropic | Community Ambassadors | ASAP | Typeform |
| Mistral | Direct outreach (EU angle) | April 7 | Sophia Yang, Head of DevRel |
| Groq | Hackathon Credits | April 7 | console.groq.com/landing/hackathon |
| MLH | Event Membership | ASAP | mlh.io/event-membership |

University GPU clusters (UPT + UVT): Can host open-source models (Llama, Mistral, DeepSeek) with zero cost and no age/consent issues. Need to confirm: what GPUs are available, sysadmin support, network access from venue.

Fallback: Buy $500 of Gemini Flash-Lite. Covers the whole event.

## Action Items

### This week (by April 7)

| # | Action | Owner |
| --- | --- | --- |
| 1 | Finalize concept — answer questions 1–8 above | All organizers |
| 2 | Recruit mentors — reach out to agentic.tm, UPT, UVT | Vlad + Bianca |
| 3 | Apply to OpenAI Hackathon Support |  |
| 4 | Apply to Anthropic Community Ambassadors |  |
| 5 | Email Mistral DevRel |  |
| 6 | Set up Groq hackathon credits |  |
| 7 | Apply for MLH Event Membership |  |

### By April 14

| # | Action | Owner |
| --- | --- | --- |
| 8 | UPT/UVT faculty: apply for Google Cloud Teaching Credits (link) |  |
| 9 | Confirm venue |  |
| 10 | Open registration |  |
| 11 | Check UPT/UVT GPU cluster availability |  |

### By May 1

| # | Action | Owner |
| --- | --- | --- |
| 12 | Prepare workshop materials |  |
| 13 | Build starter templates for students |  |

### Pre-event (May 1–14)

| # | Action | Owner |
| --- | --- | --- |
| 14 | Students create accounts (Together AI, Groq, Mistral, Google AI Studio, GitHub) |  |
| 15 | Set up credit distribution |  |
| 16 | Test all API access end-to-end |  |